## MOTHER Board PCB Serviceability – ENGG3200 (Zak Lobko)

  - Scope

    - Objectives:

      - Reduce noise from high voltage systems

      - Increase serviceability of CEN node

    - TASKS:

      - *Outlined in ‘2025 MOTHER Board Changes From 2024’ document*

        - Listed below under: 2025 MOTHER Board Changes From 2024

      - Design MOTHER Board

        - Fit to opposite side of chassis to HIP

        - TSAL DT

          - Change name to UEN

        - Keyed AT 8 pin connectors for DCDC, DEN, REAR, MOTOR CONTROLLER

        - Interpose on CEN from LVD

        - Update to new MOSFETs on cooling, brake light and sounder circuits

      - Order MOTHER Board

      - Manufacture MOTHER Board

        - Process created during semester

      - Commission MOTHER Board

        - Process created during semester

  - Resources

    - Expected budget: $150 AUD

    - Budget limit: $300 AUD

    - Where to start:

      - Read Lukes’ ENGG3200 report on creation of MOTHER Board V1.2

      - Read the relevant sections of 2025 rules that relate to the MOTHER Board node

      - Complete appropriate Zero to Heros

  - Timeline:

    - MOTHER Board ordered: 4/04/2025

    - MOTHER Board commissioned: 24/04/2025

    - Planned Integration tests:

      - MOTHER Board and HFR V4: 9/05/2025

      - MOTHER Board and BSPD V3: 15/05/2025

      - MOTHER Board and LVD V4: 16/05/2025

      - MOTHER Board and HIP V1.2: 16/05/2025

      - MOTHER Board, HIP V1.2 and BSPD V3: 22/05/2025

  - External help

    - Direct contact with Lukes for all issues encountered as well as general advice

    - Maximum 5 hours/week

  - Equipment

    - Access to all tools in the workshop and MCHA lab areas

      - MCHA lab access given upon completion of PCB and Lab Tools Zero to Hero’s

  - Dependencies

    - Relevant and realistic space on the chassis allocated

    - BSPD, LVD and HIP PCBs ready to test with by the given dates

  - Deliverables

    - MOTHER Board designed, manufactured and commissioned

      - Ready to test for the NU24/NU25 LV system integration test on NU24

        - Currently planned for 25/05/2025

      - Fully functioning by NU25 first drive

        - Currently planned for 25/06/2025

    - Knowledge transfer document detailing:

      - the design, manufacture and commission of the MOTHER Board V2 node

      - weather the new MOTHER Board V2 design increases the serviceability of the node or not

  - Due dates for deliverables (written 16/05/2025):

    - 6/06/2025 (Friday of week 13)

      - MOTHER Board V2 designed, manufactured and commissioned

    - Knowledge transfer document detailing:

      - the design, manufacture and commission of the MOTHER Board V2 node

      - weather the new MOTHER Board V2 design increases the serviceability of the node or not

  - Grading:

    - Pass: PCB designed, manufactured and commissioned; no integration tests attempted. Adequate knowledge transfer

    - Distinction: PCB designed, manufactured and commissioned; all integration tests attempted and completed. Frequent participation within the team. Exceptional knowledge transfer. PCB completely functioning with the NU25 LV System.

## 2025 MOTHER Board Changes From 2024