## GENERAL
GENERAL |  |  | Date Revised: | 2025-02-05
System | Task | Priority | Assignee | Deliverable | Due Date | Complete?

## MECH
MECH TASKS |  |  | Date Revised: | 2025-02-05
System | Task | Priority | Assignee | Deliverable | Due Date | Complete?
|  | Low |  |  |  | No

## MCHA
MCHA TASKS |  |  | Date Revised: | 2025-02-09
System | Task | Priority | Assignee | Deliverable | Due Date | Complete?
Budget | account for AV one in budget | High | Lukes | AV one cost has been accounted for in budget | 2025-02-07 | Yes
Budget | explain what Dyno cost will be put towards | High | Lukes | Cost of Dyno has been explained | 2025-02-07 | Yes
Budget | exact cos of new HV connectors put into budget | High | Lukes | exact cos of new HV connectors put into budget | 2025-02-07 | Yes
Budget | cost of OTA | High | Lukes | Cost of OTA considered | 2025-02-07 | Yes
Budget | check what interpose relay is on the LVD, and if we have spares | High | Lukes | know what interpose is on LVD and if we have spares or not | 2025-02-10 | No
Stock Count | check what sensors we have | High | Lukes | sensors that we have are filled out in stock count sheet | 2025-02-10 | No
Budget | budget for twisted pair wires for can high and low | High | Lukes | all can wires are twisted pair | 2025-02-10 | No
Week 0 | Prep for week 0 preso | Medium | Lukes | able to cohertly convey starter information about MCHA systems of car | 2025-02-14 | No
Project Scopes | Create MCHA FYP and starter project scopes - use project scope form | Medium | Lukes | FYP and starter projects made | 2025-02-14 | No
Management | Create MCHA troubleshooting and diagnostic guide | Low | Lukes | MCHA troubleshooting guide | 2025-02-14 | No
GitHub | Finish making readme file for github file structure | Medium | Lukes | readme file for github file structure complete | 2025-02-14 | No
DEN | get MoTeC repaired. Will ship MoTeC on the 24th of Feb | High | Lukes | MoTeC working again | 2025-02-24 | No
Management | create wiring pinout for entire car on KiCad | Medium | Lukes | KiCad schematic with entire pinout for all connectors | 2025-02-24 | No
Management | Create MCHA commissioning procedure | Medium | Lukes | MCHA commissioning procedure | 2025-02-24 | No
Management | Create MCHA design procedure | Medium | Lukes | MCHA design procedure | 2025-02-24 | No
Looms | BOTS switch | Medium | Lukes | order new bots switch | 2025-02-24 | No
DBC | Create NU25 DBC | Medium | Lukes | NU25 DBC is done and can be used by any PCB | 2025-04-02 | No
Teensys | Decrease clock speed of teensys to a point where they still work | Low | Lukes | clock speed of teensys deceased low enough for them to still work | 2025-05-01 | No
Looms | go back to 16mm^2 on Accum to HIP | Medium | Lukes | RMS current value for IPACK - endurance and auto X motec logs | 2025-05-01 | No
Looms | Change connector for HIP to DCDC | Low | Lukes | Change connector for HIP to DCDC | 2025-05-01 | No
Looms | 16 AWG wire on looms | Low | TBA - Snr | All looms have 16 AWG wire for their 12 V and GND | 2025-05-01 | No
Management | New LOCK OUT LOCK | Low | Lukes | new lock | 2025-05-01 | No
Accumulator | look at overcharge of cells under regen. Rated for 1.5C (30 A), but getting up to 3.5C (60 A). Check if the cells are rated to this charge | Low | TBA - Snr | Instantaneous cell rating known for the cells, either limits put in place or the instantaneous rating is high enough | 2025-05-01 | No
Accumulator | method bud 3d print for most negative | Low | TBA - Snr | method bud 3d print for most negative | 2025-05-01 | No
Accumulator | heat come from enapaq cells or busbars that connect the modules? | Low | TBA - Snr | help run test for this electronically | 2025-05-01 | No
Teensys | Implement OTA | Low | Lukes | Teensy can have code uploaded to it wirelessly | 2025-05-31 | No

## Lookup
MCHA SYSTEMS | Asignees | Complete | Priority | MECH SYSTEMS
PEN | Lukes | Yes | Low | Steering
DEN | Alec | No | Medium | Brakes
CEN | TBA - Snr | N/A | High | Suspension
HIP | TBA - Jnr |  |  | Pedal Box
LVD |  |  |  | Drivetrain
Accumulator |  |  |  | Accumulator
Management |  |  |  | Chassis
Enclosures |  |  |  | Ergonomics
Misc |  |  |  | Enclosures
Tech |  |  |  | TS Stack
Design |  |  |  | Cooling
DBC |  |  |  | Wheels and Tyres
Budget
Week 0
Looms
Stock Count
Teensys
Project Scopes
GitHub