## Sheet1
Gantt Chart - Samuel Connett | Time
| Semester 1 | [15 empty] | Exams |  | Winter Holiday |  |  |  | Semester 2 | [14 empty] | Exams |  | Summer Holidays
Tasks | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | H1 | H2 | W8 | W9 | W10 | W11 | W12 | W13 | E1 | E2 | H1 | H2 | H3 | H4 | W1 | W2 | W3 | W4 | W5 | H1 | W6 | W7 | W8 | W9 | H2 | W10 | W11 | W12 | W13 | E1 | E2 | H1 | H2 | H3 | H4
FYP Topic Selection
Choose FYP topic
Complete FYP Initiation Form
Submit FYP Initiation form confirmation email
Gantt Chart
Draft Gantt chart
Discuss draft Gantt chart with supervisor
Revise Gantt chart
Submit Gantt chart on Canvas
Draft Updated Gantt chart
Discuss updated Gantt chart with supervisor
Revise Updated Gantt chart
Submit Updated Gantt chart
NUTeams Introduction
Attend Onboarding Week 0
Complete Zero-to-Hero Training
Complete Starter project
Submit Starter project Report
Meet with Dylan for Zero-to-Hero and Onboarding Check
Inverter
Research Inverter functionality and capability
Review CM200DZ Diagnosis from Stealth EV
Install CM200DZ in NU24
Reprogram CM200DZ and retune resolver
Test CM200DZ functionality with powerbox
Test CM200DZ at Track Days
Dynamometer Improvements
Research and understand Dynamometers and Taylor DE150
Research and understand YourDyno Control Module
Design integrated Motor and Dyno E-Stop shut down circuit
Receive approval for shut down circuit and order parts
Shipping Shut down Circuit
Implement and test Shut Down Circuit
Design a Motor mount with blast shield
Receive approval for Motor mount and order parts
Shipping Motor mount
Implement and test Motor Mount
Design motor alignment mounting system
Receive approval for alignment system and order parts
Shipping alignment system
Implement and test alignment system
Design Load Testing Can Node PCB
Receive approval for Load Testing Node and order parts
Shipping Load Testing Node
Implement and test Load Testing Node
Dynamometer System Checks and Running
Review Dynamometer set up with MCHA department lead
Implement requried changes from MCHA department lead
Meet with Malcolm to safety check the set-up
Implement requried changes from Malcolm
Test the motor on the Dynamometer with expected outputs
Run the motor on the Dynamometer to acquire data
Communicate findings to the team
FYP Event
Draft FYP Event Abstract
Discuss draft FYP Event Abstract with supervisor
Revise FYP Event Abstract
Submit FYP Event Abstract
Draft FYP Event Poster
Discuss draft FYP Event Poster with supervisor
Revise FYP Event Poster
FYP Event Demonstration
FYP Reports
Draft Progress Report
Discuss draft Progress Report with supervisor
Revise Progress Report
Submit Progress Report
Draft FYP Final Report
Discuss draft FYP Final Report with supervisor
Revise FYP Final Report
Submit FYP Final Report
Competition
Train another MCHA team member on my role at comp
Attend Competition
Other Courses
AERO4100
AERO4300
ELEC2720
Industry Experience
AERO4500 (assignment due dates not yet known)
AERO4600 (assignment due dates not yet known)
Additional Course (not chosen yet)