## TEMPLATE
Tasks - Name |  |  | Date Revised: | 2024-11-01
System | Task | Priority | Assignee | Deliverable | Due Date | Complete?
|  | Low |  |  |  | No

## Lukes
Tasks - Lukes |  |  | Date Revised: | 2025-02-05
System | Task | Priority | Assignee | Deliverable | Due Date | Complete?
Budget | account for AV one in budget, explain what Dyno cost will be put towards | High | Lukes | AV one cost has been accounted for in budget. Cost of Dyno has been explained | 2025-02-07 | No
Week 0 | Prep for week 0 preso | Medium | Lukes | able to cohertly convey starter information about MCHA systems of car | 2025-02-14 | No
Management | Create MCHA troubleshooting and diagnostic guide | Low | Lukes | MCHA troubleshooting guide | 2025-02-14 | No
Management | create wiring pinout for entire car on KiCad | Medium | Lukes | KiCad schematic with entire pinout for all connectors | 2025-02-24 | No
Management | Create MCHA commissioning procedure | Medium | Lukes | MCHA commissioning procedure | 2025-02-24 | No
Management | Create MCHA design procedure | Medium | Lukes | MCHA design procedure | 2025-02-24 | No
DBC | Create NU25 DBC | Medium | Lukes | NU25 DBC is done and can be used by any PCB | 2025-04-02 | No
Looms | 16 AWG wire on looms | Low | Lukes | All looms have 16 AWG wire for their 12 V and GND | 2025-05-01 | No

## Example - Fisher
Tasks - Fisher |  |  | Date Revised: | 2024-11-27
System | Task | Priority | Assignee | Deliverable | Notes | Complete?
Vehicle Dynamics | Review Milliken and Milliken | Low | Fisher | N/A |  | No
Suspension | Pick up the a arms from Banlaw | High | Fisher | Painted a arms |  | Yes
Management | Review Johnny's foot closeouts + drawings | High | Fisher | Sent closeouts to Hancock |  | Yes
Management | Review Rishi's Scatter Shield and Chain Guard + drawings | High | Fisher | Sent parts to Hancock |  | Yes
Management | Review everyone's submitted tasks for Tech | Medium | Fisher | Data for Tech |  | No
Wheels and Tyres | Get Tyres put on rims ( waiting on tim to check with his mate and then book depending on the response) | High | Fisher | 4 new tires on rims |  | Yes
Wheels and Tyres | Buy new rims | High | Fisher | New rims |  | Yes
Enclosures | Design holder for the CEN | Medium | Fisher | Mounted CEN | A mount is modelled. Needs to be 3D printed to verify function - parts have been water cut and need to be folded | Yes
Vehicle Dynamics | Calculate values for our Dynamics (Design defence) | Low | Fisher | N/A |  | No
Vehicle Dynamics | Build a balance sheet | Low | Fisher | Balance sheet |  | No
Vehicle Dynamics | Build a driver feeback sheet | Low | Fisher | Driver feedback sheet |  | Yes
Vehicle Dynamics | Review TTC Data for the LC0 | Low | Fisher | N/A |  | No
Ergonomics | Review Adjustbale Head Rest rule | Low | Fisher | N/A |  | Yes
Steering | Paint the steering wheel shaft | Low | TBA - Jnr | Painted steering wheel shaft |  | Yes
Steering | Make a new steering rack shaft | Low | TBA - Jnr | Spare steering rack shaft |  | N/A
Cost | Cost amendment report | Low | Fisher | Prepare the cost amendment report |  | No
Cost | Complete Cost Scenario | Low | Fisher | Prepare the Cost Scenario |  | No
Powertrain | Print Tripod sander part + sand tripod down | High | Fisher | Smaller tripod roller |  | Yes
Management | Go through the design event marking and assign jobs | Medium | Fisher | Assigned jobs / roles for design |  | No
Accumulator | Speak to the machinists about putting a hole in the lid for the hatch | High | Fisher | Knowledge on how to cut the hatch in the |  | Yes
Accumulator | Bolt the accumulator in the car and check that EVP is higher than the lid | High | Fisher | N/A |  | Yes
Steering | Get the gearbox shaved down to under 50 mm | High | Fisher | Compliant steering for tech | Was done last year I measured it wrong | Yes
Misc | Check Aaron's Jig for NU 16's wing | High | Fisher | Let him know what needs changing |  | Yes
Steering | Adjust steering cover and print it | High | Fisher | Printed steering column cover |  | Yes
Vehicle Dynamics | Use TTC data to find where our setup will give max lateral grip (Fy) | High | Fisher | Potential set up for the car |  | No
Powertrain | Buy new sprockets and check chain count | High | Fisher | New sprockets - found the sprockets need to buy them |  | Yes
Misc | Buy new bolts to make things compliant | High | Fisher | New bolts |  | Yes
Misc | Buy a black paint pen to fix up where the paint has chipped | Medium | Fisher | New paint marker |  | Yes
Powertrain | Print new jig to test centre to centre of the stretched chain | High | Fisher | Improved centre to centre |  | Yes
Powertrain | submit drawings for the powertrain and scatter shield | High | Fisher | Submitted Drawings |  | Yes
Cooling | Submit drawings for the catch can and the radiator weldment | High | Fisher | Submitted Drawings |  | Yes
Steering | Buy new jam nuts | High | Fisher | Jam Nuts - PO in Asana |  | Yes
Misc | Print all rules Enquiries | High | Fisher | emails - ask tim to do this as well |  | No
Accumulator | Submit drawings for the bus bar methode bud | High | Fisher | Submitted Drawings |  | Yes
Misc | Making a map for th4e figure 8 circuit | High | Fisher | Map |  | Yes
Misc | Call Hoosier to see about the tires | High | Fisher | Knowledge on tyres |  | Yes
Misc | Fix the track layout for the Figure 8 | High | Fisher |  |  | Yes
Design | Review - what are our major package changes and how does that affect the car? | High | Fisher | Booklet Images and design defence |  | No
Design | Images of the track and the wheelbase of the car | High | Fisher | add them to the design booklet |  | No

## Lookup
System | Asignees | Complete | Priority
PEN | Lukes | Yes | Low
DEN | Alec | No | Medium
CEN | TBA - Snr | N/A | High
HIP | TBA - Jnr
LVD
Accumulator
Management
Enclosures
Misc
Tech
Design
DBC
Budget
Week 0
Looms