# NU Racing’s 2025 MCHA Team Scopes/Projects

This document contains the preferred amount of FYP Scopes and Directed Projects for NU Racing 2025’s team.

Assumptions:

- Number of FYPs: 5

- Number of Directed Reading/Extracurricular: 2

FYP Scope contain:

- Starter project

- Scope for the year

Directed Reading/Extracurricular Projects contain:

- Scope for a semester project

## FYP Scopes and Starter Projects

- Data Engineer– FYP

  - Starter Project

    - Read Jackson’s report

    - Read Nick Lyall’s report for amplifier circuit for wheel speed sensors

      - Read datasheet to see if this circuit is needed at higher revs, as Nick discovered this using a 3d printed mount to imitate a wheel

        - Failing datasheet retrieval, attempt to use Nick’s set up with a drill to see if higher revolutions can be achieved.

    - Mount wheel speed sensors (3d printed)

      - Design 3d printed mount to attach to potentially all 4 wheels of NU24

        - So that if project is finished, sensors can be easily tested

        - Do the front two first wheel speed sensors first

    - Creation of loom to plug into EXPANSION Board

      - Pinout of OEM connector researched

      - Pinout of new DT connector correct and able to interface with EXPANSION Board

    - Wheel speed sensor data is able to be read from MoTeC

      - Create 4 messages in NU25 DBC file for wheel speed sensors (one for each wheel), with correct scaling, offset, bit length and value range

      - Implement code for wheel speed sensors on the EXPANSION Board

        - With data from wheel speed sensor sent using the message from previous dot point

      - Configure MoTeC to read and display new message

    - Deliverable:

      - Front two wheel speed sensors mounted

      - Working with the EXPANSION Board on CAN King and (hopefully) MoTeC

  - DEN:

    - Resize to chassis (might not have to?)

    - All naming of AMS to BMS

    - Change from DT 8 pin to AT 8 pin keyed connector for CEN connection

  - EXPANSION Board

    - Size CAN lines correctly

    - Fix ground plane (not have big breaks)

    - Transfer SWEN functionality

      - Includes: dials for torque setting, switch for regen (implement a way so that the dial/switch are in the correct position after unplugging and plugging the board in)

    - Temperature sensors for radiator

      - Create loom to connect to them (already in radiator)

      - DBC file and MoTeC updates

    - Implement shock pots, wheel speed and steering angle

  - Strain gauge research/implementation

  - In charge of monitoring and managing MoTeC at track days

  - Mount shock pots and steering angle sensor

  - Work with HV Engineer for wheel speed sensors

- HV Systems-Powertrain – FYP

  - Starter Project Ideas

    - Read and understand both Hayward’s and Dawso’s reports?

    - Implement any recommendations from Hayward’s report

      - Implement pack current derating at cell/pack temperatures over 50 degrees.

        - PEN code

          - Use either maxsegtemp or mincellvol/maxcellvolt

          - Derate from the 3 degrees under the max temperature rating of the VTC6

          - Limit current down to ~30A under high temperatures. Shut down all current above 60 degrees

    - Learn how to charge the car

    - Deliverable:

      - Current derate at high temperatures works as intended

        - Test to show it off could include having the max allowable temperature to be set to a low value (eg 30 degrees) and have a track day where the car is driven hard, if it works correctly, then current will be limited and cut out to the driver upon approaching and reaching the set limit

      - Know how to charge the car

  - Learn how motor controller and powertrain work – read Hayward’s report and MC preso

  - Dynamometer

    - Create Load Testing Node

    - Read Josh Dawson report on the dyno

    - Implement as much as possible for the dyno

    - If all goes to plan, will be able to test load test HV systems on the dyno without using the car

      - Mapping power curves

  - Know how to charge the car

  - Implement recommendations from Hayward’s report

  - Tune motor (big maybe)

  - Changes to powertrain due to LSD change

  - Launch control implementation/research (kind of traction control)

    - With wheel speed sensors, implement launch control on the PEN

    - Work with Data Engineer

  - Hub motor research and implementation on future NU Racing cars

- Accumulator – FYP

  - Starter Project

    - Read Daniel’s report

    - Design and commission new AIL, breakout board mounting, implement change from Ivo’s report

    - Learn how to charge the car

    - Deliverable:

      - AIL ordered (with LTspice or breadboard test)

      - Know how to charge the car

  - Service and refine the Energus Accumulator

    - Fix AMS Fault (maybe new version of CANaMons)

  - Change top plate fuse holders

  - New AIL/voltmeter

  - New LVD

    - Interpose from LVD to CEN

    - Use of IRLB3813 MOSFET for cooling circuit (gather information from CEN engineer) or use automotive relay

    - Investigate high current draw of accum fans

  - NU26 Accumulator

    - Design new voltage tap and temperature monitoring for pouch cell accumulator

    - Pouch cell testing and validation

- AV.One – FYP – Jayden Horvath

  - Starter Project

    - Read Lena’s and Sebastian Scott’s reports

      - ‘Past_Reports’ folder within ‘Racing-AV1’ GitHub.

    - LVD rework to enable use of charger with AV.One

    - Troubleshoot DCDC

    - Deliverable:

      - New LVD ordered and found issue with DCDC

  - Implement and test 2x Raspberry HQ Cameras for stereo vision

  - Investigate use of either Marine’s LiDAR or use of spare LiDAR that is somewhere on campus – refer to Malcolm for details

  - Attempt to implement as many Autonomous Advancements as possible from Lena’s Report (section 8.2.)

    - Contact UQ’s autonomous race team on issues encountered and/or direction

      - madeleine.warner@uqracing.com

      - james.talkington@uqracing.com

## Directed Reading Scopes

- PEN/BSPD and potentially TSAL_Discharge – Directed – Jayson

  - Where to start:

    - Read Bushy’s reports the BSPD and the TSAL_Discharge breakout boards

    - Lukes’ report on why the resistor voltage divider was a time-consuming idea. With too many variables to account for during the commissioning process.

    - Read the section of PEN from Joshua Hayward’s report, to gain a brief understanding of the PEN

    - Read Josh Dawson’s report

      - Mainly:

        - 4.4 Proposed Modifications

        - 4.5 CAD/Schematic/PCB/Code

        - 4.6.3 Charger V1 PCB

        - 4.7.1 ECU Verification

  - BSPD

    - Remove voltage divider for C_REF. Replace with potentiometer, as this is easier for someone to understand how to tune it correctly

  - PEN

    - Fit to pedal box

    - Add capacitors to brake sensor inputs

    - Investigate need for Zener diodes, and if possibly removing them

  - TSAL_Discharge

    - Change current naming of red to amber on Bushy’s V3 and order

    - Potentially implement green light turning off while red is flashing

  - Charger

    - Add new HV connectors

    - Fix oopsie wire on PCB

- HIP – Directed or Extra – Mia (is ENGG3200 in SEM 2)

  - Read Jackson’s report?

  - All naming of HVD to MSD

  - New Master Switches (footprint will change)

  - HV connector interlock (part of the mech enclosure role?)

  - Change from DT connector to one that is rated for higher voltage for DCDC to HIP connector

- Directed

  - HFR

    - Implement BMS-IMD Tractive System Status Indicator fault detection circuit on this board

      - Read 2025 rules and compare them to 2024’s rules to understand the change

      - Research circuit to implement this change

      - Design circuit

        - AND gate for BMS and IMD fault detection

        - 555 timer circuit for 2-5 Hz signal generation (research correct circuit (555 timer datasheet), but ultimately use the one that is on the TSAL_Discharge board (use DMN6140L for all MOSFETs)

        - MOSFET to switch outputted gnd signal

        - Rough outline of circuit in obsidian notes

      - LTSpice the circuit

      - Breadboard the circuit

        - Red Flash of TSSI could be just a THT LED?

      - Correct PCB to accommodate for circuit

        - Increase input/output of header pins by 1 on each side

      - Order PCB

    - Implement green light turning off while red is flashing

      - Potentially make a second circuit to account for this possibility

        - Rough outline of circuit in obsidian notes

    - LTSpice/Breadboard test

  - Deliverable:

    - HFR with working and tested BMS-IMD fault detection circuit

  - CEN Iteration

    - TSAL DT

      - Change name to UEN

      - Make it an 8-pin connector (to route new red switch ground signal)

    - Route TSAL_GREEN_SWITCHED_GND (rename) to HFR breakout

  - Ready To Move Light implementation (while PCBs are on order)

    - Order and commission a light that meets DOT FMVSS 108

    - Change loom

    - Design mounting for 2x amber DOT FMVSS 108 lights on the car (one facing forward and one facing backwards (aft))